Division 02 - Site Work

02 000 General

02 080 Hazardous Material Abatement

02 081 Asbestos Abatement

Scope of Work for Ogden High School, February 2, 2011

1.  Flooring Removal

- Contractor shall remove all floor tile and all associated adhesive mastic from the building as shown on the attached floor plans. There is approximately 33,000 square feet of flooring to be removed. This material contains up to 25% chrysotile asbestos.  These materials are currently non-friable.

- Contractor shall remove the flooring as an OSHA Class II operation.

2.  Surfacing Material

A.	Contractor shall remove all surfacing material from the building as shown on the 	attached floor plans. There is approximately 42,500 square feet of surfacing to be 	removed. This material is friable when removed. It has been painted and Contractor 	shall secure an Alternative Work Practice from DAQ, as this material cannot be 	wetted prior to disturbance.

3.  Window Caulking

A.	Contractor shall remove the windows from the building as shown on the attached 	plans. The window caulk contains over 1% chrysotile asbestos. There are 	approximately 300 windows to be removed. This material is currently non-friable.

B.	Contractor shall cover the window openings on the first floor with plywood to prevent 	unauthorized entry into the facility at the conclusion of Contractor’s work.

4.  Sink Undercoating Material

A.	Contractor shall remove the sinks with ACM undercoating material from the building as shown on the attached plans. This includes 12 sinks to be removed. These materials are currently non-friable.

5.  Sheet Vinyl Flooring

A.	Contractor shall the sheet vinyl flooring from the building as shown on the attached 	plans. There is approximately 160 square feet of material to be removed. This 	material has a backing containing approximately 65% chrysotile asbestos. This 	material will be friable during removal.

6.  Asbestos-Cement Counter Tops

A.	Contractor shall remove the asbestos-cement counter tops as shown on the 	attached plans. These materials contain greater than 1% asbestos and are 	currently non-friable. There is approximately 1,000 square feet of non-friable 	material to be removed.

B.	Contractor shall clean the removal area of any suspect ACM debris after removal of 	counter tops.

7.  General

A.	Contractor shall provide a copy of the NESHAP/Utah notification form (if applicable) to Consultant as soon as possible after Contractor’s submission to DAQ.

B.	Contractor shall perform daily air monitoring during all friable work and post all personal air sampling results from the project at the job site no later than the end of the shift the following work day.

C.	Contractor shall provide Consultant with his work plan no later than one week prior to the start of the project. The plan shall be faxed or otherwise delivered to the offices of R & R Environmental, Inc., to the attention of Eldon C. Romney, 47 West 9000 South, #2, Sandy, Utah  84070, FAX:  (801)352-2381.  This plan shall show anticipated locations for the HEPA units and decontamination facility, and a projected time schedule.

D.	Contractor shall ensure his electrical design and plans are compatible with the facility operation and with the National Electrical Code.  Contractor shall use only electrical equipment rated for work in damp environments in the containment area.  Any equipment not labeled "rated for work in damp environments" may not be permitted in the containment.

E.	Contractor shall ensure all equipment brought onto the site is free of suspect asbestos-containing material (ACM).  Consultant may disallow use of equipment with suspect ACM.

F.	Contractor shall comply with Owner’s projected schedule needs. Phase 1 of the project will begin April 4, 2011 and last 2 weeks. Phase 2 will start approximately June 1, 2011 and last approximately 8 weeks.

G.	Reserved.

H.	Contractor shall take appropriate steps to safeguard existing items, which are scheduled to remain in the facility.  These items may include existing fiberglass insulation, ducting, conduits, etc.

I.	Contractor shall provide a certificate of weight and measure (or other certification acceptable to the Industrial Hygiene Consultant) for all ACM waste taken from the site.  The certification shall list gross, tare and net weights for all ACM waste.  Contractor shall also provide, on Contractor's letterhead, a listing of each manifest used for the project, by number and waste tonnage (in pounds) specific to that manifest.  Listing shall show if ACM was disposed of as regulated waste, non-hazardous or any other state-approved category of waste.  This information shall be provided prior to, or at the time of invoice submission.

J.	All poly sheeting used by Contractor on the project shall be of the fire-retardant type.  Each containment shall be built with a clear plexi-glass window no smaller than two feet square, which allows viewing of the work from outside the regulated area.

K.	Smoking is not allowed on the Owner's property.  Any violation of this provision is grounds for expulsion of the offending party from the work site for the work’s duration.

L.	The most stringent regulations in effect for the work site shall apply.  Contractor shall determine the extent of city, county, AQMD, state, federal and all other applicable regulations and perform the work in compliance with these regulations.

M.	Reserved.

N.	Contractor shall provide the Industrial Hygiene Consultant with MSDSs for all materials used on their work site.

O.	Contractor shall limit his work day to ten hours in length unless agreed to in writing by the Industrial Hygiene Consultant.  If longer shifts are agreed to, Contractor agrees to reimburse Owner for all additional expenses incurred as a result of the change in schedule (these expenses include additional Industrial Hygiene Consultant personnel expenses).

P.	Contractor shall provide an English-speaking interpreter on-site any time Contractor personnel are non-English-speaking.

Q.	Electrical extension cords shall be suspended off the floor of any regulated area.  Contractor shall not use any existing electrical outlet in any regulated area (appliances or cords may not be plugged through the containment wall).

R.	Removed ACM shall be cleaned up and bagged on a continual basis.  No removed ACM shall be left un-bagged at the end of the work-day.  All waste shall be disposed of at an in-state waste facility unless agreed to in writing by the Industrial Hygiene Consultant prior to transport.

S.	Contractor shall install and maintain a job telephone at Contractor's expense.  Telephone shall be operational prior to disturbance of any ACM.  Contractor shall be fully responsible for all charges to this telephone.

T.	Contractor shall provide chemical toilets on the job site for Contractor's personnel, the Industrial Hygiene Consultant and any authorized visitors.  Contractor shall ensure these toilets are maintained appropriately and in a hygienic manner.  Contractor shall clean and furnish the toilets at least daily.

U.	Contractor shall utilize only “slinky-type” flex duct on HEPA units where the exhaust ducting goes around corners or where bends could otherwise crimp ducting, potentially decreasing its efficiency.